## Team_Members_Info
Team Member List
No | Name | StudentID | Major | Email | Phone Number | Github User
1 | Duong Nguyen Dang | 105508444 | Artificial Intelligence | 105508444@student.swin.edu.au | (+84) 888726543 | DangJohnFA
2 | Nguyen Quang Khai | 105560512 |  | 105560512@student.swin.edu.au | (+84) 908501202 | NQKAIR1202
3 | Lu Nhat Hoang | 105234956 | Software Development | 105234956@student.swin.edu.au | (+84) 911391741 | nha4110
4 | Le Xuan Ny | 105680151 | Artificial Intelligence | 105680151@student.swin.edu.au | (+84) 837665778 | angelica000329
5 | Truong Ngoc Gia Hieu | 105565520 |  | 105565520@student.swin.edu.au | (+84) 947979438 | hieugia090806
6 | Pham Nguyen Minh Hoang | 105543500 |  | 105543500@student.swin.edu.au | (+84)932626167 | HGProGFG

## Weekly Tasks
Weekly Tasks
No | Tasks | Objective | Description | Start Date | Due Date | Responsible | Resource | Status | Material | Note | Youtube Link
Week05 (Oct 12th - 18th)
Document: Project Proposal
1 | Write SUMMARY section | Provide a concise executive overview of the project scope and context. | - What core business/operational problem does this project solve for VIB - What is the proposed solution (e.g., an internal knowledge retrieval assistant integrated into Slack)? - What is the primary purpose and scope of this project proposal/report? | 2026-10-11 | 2026-10-12 | Hieu | Google Docs | Completed | Project Brief |  | N/A
2 | Write DESIRED OUTCOME section | Define the tangible deliverables and expected performance metrics. | - What does the final completed deliverable look like (qualitative outcome)? - What specific key performance indicators (KPIs) measure success (quantitative outcomes, e.g., reduced search latency, answer accuracy)? - What direct value does this system bring to VIB's internal staff | 2026-10-11 | 2026-10-12 | Ny |  | Completed
3 | Write ACTION TO COMPLETE section | Outline the specific steps and implementation methodology required to achieve the goal. | - What are the primary execution phases from initiation to project completion? - What detailed technical actions must be taken (e.g., data ingestion, vector indexing, access control verification, interface integration)? - What testing and user feedback loops will be conducted to validate the system? | 2026-10-11 | 2026-10-12 | Khai |  | Completed
4 | Write BENEFITS OF PROJECT section | Articulate the strategic and operational value proposition for the organization. | - How does the system optimize daily workflows and minimize context switching friction for internal employees? - How does the solution improve enterprise knowledge management and data security compliance? - What are the long-term organizational benefits in terms of productivity and cost efficiency? | 2026-10-11 | 2026-10-12 | Minh Hoang |  | Completed
5 | Write PROJECTED SCHEDULE section | Establish a clear timeline and milestone breakdown. | - What is the chronological timeline and milestone breakdown from Week 5 to Week 11? - What are the specific deadlines for major project deliverables? - What task dependencies exist across the planned activities? | 2026-10-11 | 2026-10-12 | Nhat Hoang |  | Completed
6 | Write PROJECTED BUDGET section | Estimate financial requirements and cloud infrastructure expenses. | - What is the estimated cost breakdown for cloud infrastructure (e.g., AWS services, vector database, LLM API usage)? - Are there any software, tool, or licensing expenses required? - What cost-optimization strategies are planned to ensure financial feasibility? | 2026-10-11 | 2026-10-12 | Dang |  | Completed |  | Done by Hieu
7 | Write PROJECTED TEAM AND RESOURCE REQUIREMENTS section | Define team member roles, technical prerequisites, and support channels. | - What are the specific roles and responsibilities assigned to each team member? - What technical resources and environments are required (e.g., AWS environment, Slack API credentials, Confluence access)? - What external guidance or support is needed from mentors and academic advisors? | 2026-10-11 | 2026-10-12 | Hieu |  | Completed
Document: Project Charter
8 | Write PROBLEM OR ISSUE section | Identify and analyze internal knowledge fragmentation across Confluence documentation sites, operational search latencies, and communication bottlenecks at Vietnam International Bank. | - What specific internal knowledge fragmentation challenges exist across VIB Confluence sites and corporate documentation? - How do manual document searches and keyword based search limitations impact employee retrieval latency and operational productivity? - Why is a centralized, Slack integrated Retrieval Augmented Generation assistant necessary to solve these enterprise communication bottlenecks? | 2026-10-14 | 2026-10-16 | Ny | Google Docs | Completed | Project Brief |  | N/A
9 | Write PURPOSE OF PROJECT section | Define the core goals, operational rationale, and strategic target outcomes of delivering a Slack integrated Retrieval Augmented Generation assistant for Vietnam International Bank. | - What is the primary purpose and overarching strategic goal of developing this Slack integrated knowledge assistant for VIB? - How does the system aim to transform static internal documentation into an active, conversational knowledge platform? - What specific target outcomes in terms of productivity, search efficiency, and access security will define project success? | 2026-10-14 | 2026-10-16 | Khai |  | Completed
10 | Write BUSINESS CASE section | Establish the financial rationale, return on investment, operational value, and risk mitigation strategies to justify the adoption of the Slack integrated knowledge assistant at Vietnam International Bank. | - What are the financial, operational, and productivity justifications for implementing this automated RAG assistant at VIB? - How does the proposed solution minimize capital expenditure during Phase 1 while ensuring clear scalability and return on investment for Phase 2 enterprise deployment? - What strategic risks, compliance factors, and data security benefits support the business case for adopting this Slack integrated solution? | 2026-10-14 | 2026-10-16 | Minh Hoang |  | Completed
11 | Write GOALS/METRICS section | Define specific, quantifiable project objectives and evaluation metrics to measure system accuracy, retrieval latency, channel security compliance, and operational impact at Vietnam International Bank. | - What are the specific, measurable quantitative goals for document retrieval accuracy, answer precision, and system latency? - How will compliance with Slack channel whitelist restrictions, user adoption rates, and reduction in search time be evaluated? - What qualitative metrics and feedback mechanisms will be used to benchmark success during local proof of concept and enterprise testing? | 2026-10-14 | 2026-10-16 | Nhat Hoang |  | Completed
12 | Write EXPECTED DELIVERABLES section | Specify all tangible software artifacts, technical documentation, architectural models, and testing reports to be delivered upon project completion for Vietnam International Bank. | - What tangible technical artifacts, such as source code repositories, automated data ingestion pipelines, and vector database indexes, will be delivered? - What specific conversational Slack app bot features, channel whitelist configurations, and operational documentation will be handed over? - What academic reports, system architecture diagrams, and end to end performance validation test suites are required for final project sign off? | 2026-10-14 | 2026-10-16 | Dang |  | Completed
13 | Write WITHIN SCOPE section | Define the boundaries of technical features, automated data ingestion pipelines, RAG engine capabilities, Slack bot configurations, and local validation testing included within the current project phase. | - What specific internal documentation sources, Confluence spaces, and data ingestion pipelines are officially included within the project scope? - Which technical components, such as vector indexing, RAG retrieval frameworks, Slack app bot interfaces, and channel whitelist restrictions, will be fully developed? - What functional testing procedures, local proof of concept evaluations, and baseline performance benchmarks are in scope for delivery? | 2026-10-14 | 2026-10-16 | Hieu |  | Completed
14 | Write OUTSIDE OF SCOPE section | Explicitly delineate technical boundaries, excluded features, enterprise core integrations, and future expansion phases not included in the current project deliverable. | - What specific enterprise channels, communication platforms outside of Slack, and external third party tools are explicitly excluded from the current phase? - Which complex core banking system integrations, automated transaction workflows, and multi tenant role management features are reserved for future deployment? - What full scale cloud infrastructure investments, paid enterprise API quotas, and continuous real time database syncing mechanisms fall outside the current proof of concept scope? | 2026-10-14 | 2026-10-16 | Ny |  | Completed
15 | Write TENTATIVE SCHEDULE section | Outline the chronological timeline, key project milestones, phase transitions, and deliverable deadlines spanning from week five through week eleven for the system development life cycle. | - What are the specific start dates, finish dates, and major technical milestones scheduled across the seven week project timeline? - How are development activities structured chronologically across pipeline engineering, vector indexing, RAG integration, Slack bot setup, and system testing phases? - What specific target deadlines and review checkpoints are established to monitor progress and ensure timely handover of the final prototype? | 2026-10-14 | 2026-10-16 | Khai |  | Completed
16 | Write RESOURCES section | Identify and categorize all human resources, software frameworks, hardware infrastructure, cloud APIs, academic reference materials, and external guidance necessary for successful project execution. | - What human resources, team role allocations, and technical skill sets are assigned across the six project members? - What specific software libraries, vector databases, orchestration frameworks, and Slack API tools form the core development stack? - What hardware compute capabilities, academic literature bases, and external guidance from advisors or enterprise mentors are required to support development? | 2026-10-14 | 2026-10-16 | Minh Hoang |  | Completed
17 | Write COSTS section | Estimate direct and indirect financial requirements, software licensing options, development hardware utilization, and future cloud infrastructure operational expenses for the platform. | - What is the financial cost breakdown for local development, open source software utilization, and student hardware resources during Phase 1? - What specific cloud compute infrastructure, managed vector storage, and commercial model API licensing costs are projected for Phase 2 enterprise scaling? - What cost optimization strategies and open source alternatives are implemented to achieve zero direct capital expenditure during the initial proof of concept phase? | 2026-10-14 | 2026-10-16 | Nhat Hoang |  | Completed
18 | Write BENEFITS AND CUSTOMERS section | Identify key internal stakeholders and target customer groups while articulating the tangible operational, strategic, and efficiency benefits delivered to Vietnam International Bank. | - Who are the primary internal customers, end user groups, and key enterprise stakeholders benefitting from this Slack integrated assistant at VIB? - What specific productivity gains, search latency reductions, and operational advantages will bank personnel experience in their daily workflows? - How does the system enhance data governance, internal communication efficiency, and overall organizational knowledge accessibility across various bank departments? | 2026-10-14 | 2026-10-16 | Dang |  | Completed |  | Done by Hieu
19 | Write RISKS, CONSTRAINTS, and ASSUMPTIONS section | Analyze potential technical and operational risks, document mandatory project constraints, and define core foundational assumptions required for successful system deployment. | - What potential technical risks, such as model hallucinations, retrieval inaccuracies, network latency, or API rate limits, could impact project delivery, and how will they be mitigated? - What mandatory project constraints exist regarding zero capital expenditure budget for Phase 1, strict Slack channel whitelist security, and the seven week academic timeline? - What baseline assumptions are made regarding Confluence document availability, team development hardware capabilities, and uninterrupted access to developer tier API services? | 2026-10-14 | 2026-10-16 | Hieu |  | Completed
Week06 (Oct 19th - 25th)
20 | Write Project_Scheduled | Establish a structured seven week project timeline detailing core milestone phases, critical path activities, deliverable deadlines, and resource allocation schedules for the enterprise assistant development. | - What primary project phases, key delivery milestones, and specific calendar deadlines are structured across the strict seven week academic lifecycle? - How are critical technical workstreams, including REST Confluence data pipeline implementation, RAG engine integration, Slack Socket Mode setup, and testing verification, mapped chronologically? - What baseline scheduling constraints and progress tracking mechanisms are established to ensure zero schedule slippage and on time client handover? | 2026-10-22 | 2026-10-23 | Nhat Hoang | N/A | Completed | N/A |  | N/A
21 | Write Announcement Email | To formally notify the course lecturer regarding the addition of a new team member, update the official project roster, and ensure clear alignment on role assignments and a ccountability for upcoming deliverables. | - How does the high level architecture facilitate end to end data flow between the Slack Socket Mode client, security middleware, vector search retrievers, and LLM reasoning services? - How is the data ingestion pipeline structured to execute REST API extraction from Confluence, HTML to Markdown conversion, multimodal body image processing, and vector database indexing? - What specific modular software design pattern is applied to separate presentation handlers, access control security logic, core RAG capabilities, and data storage services into isolated layers? | 2026-10-22 | 2026-10-23 | Hieu |  | Completed
22 | Write Announcement Email | To formally notify the course lecturer regarding the addition of a new team member, update the official project roster, and ensure clear alignment on role assignments and a ccountability for upcoming deliverables. | - How does the high level architecture facilitate end to end data flow between the Slack Socket Mode client, security middleware, vector search retrievers, and LLM reasoning services? - How is the data ingestion pipeline structured to execute REST API extraction from Confluence, HTML to Markdown conversion, multimodal body image processing, and vector database indexing? - What specific modular software design pattern is applied to separate presentation handlers, access control security logic, core RAG capabilities, and data storage services into isolated layers? | 2026-10-22 | 2026-10-23 | Hieu |  | Completed
23 | Enter Slack and Confluence Email | To establish isolated Free-tier Sandbox environments on Slack and Confluence, providing an unconstrained playground to configure API integrations, build custom bot permissions, and test data ingestion pipelines without dependency on VIB enterprise infrastructure restrictions. | - Creating a dedicated Confluence Free Space (VIB-Mock-Knowledge) to host mock enterprise documentation, complex tables, and multimodal assets. - Setting up a dedicated Slack Free Workspace with Socket Mode enabled, custom app manifest definitions, and necessary OAuth scopes. - Configuring API access keys, Webhook endpoints, and developer tokens to connect backend services for data crawling and event handling. | 2026-10-22 | 2026-10-23 | Hieu |  | Completed |  | Team members MUST accept the initation
24 | Add Github User | To grant repository access to all team members, establish version control access permissions, and prepare a collaborative Git environment for seamless code sharing and tracking across frontend, backend, and data pipeline tasks. | - Sending GitHub repository invitations to team members using their registered GitHub handles/emails. - Assigning appropriate repository roles (e.g., Write/Maintainer access) to ensure proper branch operations. - Verifying repository visibility and configuring basic branch protection rules for the primary codebase. | 2026-10-22 | 2026-10-23 | Hieu |  | Completed |  | Team members MUST accept the initation
25 | Take Note Meeting Minutes (MoM) | To accurately capture and document key discussions, architectural decisions, technical agreements, and action items during team syncs and mentor meetings, ensuring transparent alignment and tracking accountability across all members. | - Documenting meeting metadata (date, time, attendees, and agenda items). - Summarizing core technical decisions, architectural choices (e.g., Slack Socket Mode, RAG pipeline structure), and risk discussions. - Listing explicit Action Items with assigned owners and deadlines to synchronize directly with the team's task board. - Archiving and sharing the finalized MOM in the shared team repository (Confluence/Google Drive) for quick reference. | 2026-10-22 | 2026-10-23 | Ny | Confluence | In Progress |  | Push to Confluence
26 | Make Slide for Presentation | To design and synthesize a structured, visual presentation deck that effectively communicates the team's project charter, system architecture, technical specifications, and weekly milestones to the lecturer/mentor. | - Structuring core topics: Project Scope, System Architecture (Slack Framework, Middleware Logging, RAG Pipeline), and Data Ingestion specs. - Visualizing technical components using diagrams (e.g., Socket Mode workflow, data crawling formats, and team task allocation). - Aligning content with weekly progress updates, risks/mitigations, and next steps for Step 1 execution. - Formatting slides for visual clarity, consistency, and professional presentation readiness. | 2026-10-22 | 2026-10-23 | Dang | Canva | Completed |  | Must know what group is doing
27 | Figure out how to Set up Framework for Bot in Slack and then choose the best one later | To construct the foundational Slack bot application framework using Slack Bolt SDK and Socket Mode, establishing a verified, two-way event communication channel between Slack UI and the Python backend service. | - Creating and registering the Slack Bot App in api.slack.com within the Sandbox workspace. - Configuring Socket Mode, app manifests, and granting essential OAuth Bot Token Scopes (app_mentions:read, chat:write, channels:history). - Developing a lightweight Python application (slack-bolt) to receive @mention events and return baseline response payloads. - Verifying end-to-end event connectivity and securing environment configurations (SLACK_BOT_TOKEN, SLACK_APP_TOKEN) prior to adding middleware and RAG components. | 2026-10-22 | 2026-10-24 | Minh Hoang | Gooogle Docs | In Progress | Slack | Khai and Nhat Hoang assist Draft on Google Docs and choose the best one later | https://www.youtube.com/watch?v=mOUivLyliTQ https://www.youtube.com/watch?v=oDoFvpDftBA https://www.youtube.com/watch?v=HOnEiUSqYbU https://www.youtube.com/watch?v=zA8Nn7wGeXk
28 | Set Up Branches for Github | To establish a structured, secure, and standardized Git branching workflow on GitHub, enabling safe multi-developer collaboration, enforcing code reviews, and ensuring the stability of the core application code base throughout development. | Define and implement the Git branching strategy to be used for development. Key deliverables include: - Adopting a branching model (e.g., GitHub Flow, Git Flow, or a customized model) suited for the RAG Bot project. - Creating and configuring foundational branches, typically main (for stable, production-ready code) and GUIDELINES for ephemeral branches (e.g., feature/, bugfix/, hotfix/). - Configuring Branch Protection Rules for the main branch. This must enforce standard practices such as: + Requiring Pull Request reviews and approvals before merging. + Requiring status checks (CI/CD pipelines, if applicable later) to pass. + Restricting direct pushes to protected branches. - Documenting and communicating the workflow to all team members to ensure smooth adoption and compliance. | 2026-10-22 | 2026-10-23 | Hieu | Github | Completed |  | - Strictly no direct pushes to the main branch (this keeps our production codebase clean, stable, and ready for showcase at any time). - Branch /develop is the highest branch we will directly touch or merge into. (All code goes through individual feature branches first). - Strictly no direct pushes or merges to the main branch (this keeps our production codebase clean, stable, and strictly reserved for final showcases). | N/A
29 | Edit Cover Page section | Complete the cover page so the document is ready for submission. | - Fill in the unit code, unit name and submission date, which are currently placeholders. - Remove all the italic instruction texts before submitting. | 2026-10-23 | 2026-10-24 | Hieu | Google Docs | Completed |  | Fill in the Unit Code, Unit Name, and Submission Date
30 | Write Acknowledgement of Country section | Recognise the Traditional Owners of the land where each member completed the work. | Each team member names the Traditional Owners of the land they lived on while doing this work (if living in Australia), with a link to the AIATSIS map. | 2026-10-23 | 2026-10-24 | Hieu |  | Completed
31 | Write Team Profile (Table 1) section | Understand each member’s strengths so work can be allocated well. | Summarise each student’s technical skills, soft skills, communication style, teamwork experience and other relevant background in Table 1. | 2026-10-23 | 2026-10-24 | Khai |  | Not Yet
32 | Write Team Role (Table 2) section | Assign a suitable role to each member. | Based on the profiles, each student chooses a team role and gives a justification for why it suits them (Table 2). | 2026-10-23 | 2026-10-24 | Minh Hoang |  | Completed
33 | Write TeamWork Roadmap section | Set how the team will work together week to week. | - Describe the weekly meeting time and mode, communication platforms, response-time expectations, internal deadlines and the revision process. - Explain how tasks are estimated, assigned and monitored. List the tools used (a project management board such as Trello, Jira or a shared Excel is compulsory, with evidence) and the rationale for each. - Set rules for communication, expected behaviour and fallback plans. | 2026-10-23 | 2026-10-24 | Nhat Hoang |  | Completed
34 | Write Document Management section | Keep shared files organised and avoid version conflicts. | Describe how shared documents are version-controlled and managed (storage location, naming convention, who edits and reviews). | 2026-10-23 | 2026-10-24 | Dang |  | Completed
35 | Write Risk Mitigation section | Identify risks early and prepare responses. | - Present a risk register covering skill gaps, member unavailability and other risks. - For each risk, state its impact on the team and a mitigation plan. - The team revisits the register throughout the project. | 2026-10-23 | 2026-10-24 | Hieu |  | Completed
36 | Write Problem Statetment section | Define the problem the project solves. | Give a high-level summary of the problem and state the aim, purpose and objectives of the project. | 2026-10-23 | 2026-10-24 | Ny |  | Not Yet
37 | Write Scope section | Set clear project boundaries. | State what is in scope and what is out of scope. | 2026-10-23 | 2026-10-24 | Khai |  | Not Yet
38 | Write Stakeholder section | Identify everyone affected by or involved in the project. | List each stakeholder (e.g. client, supervisor) and their role or interest. | 2026-10-23 | 2026-10-24 | Minh Hoang |  | Completed
39 | Write High-Levrl Requirements section | Capture what the system must do and the context it sits in. | - Explain the context (upgrade or replacement, new system or prototype, standalone or part of a larger system, ideally with a simple diagram). - List the functional, non-functional and other known requirements. | 2026-10-23 | 2026-10-24 | Nhat Hoang |  | Completed
40 | Write Solution Approach section | Propose how the system will be built. | Describe the proposed solution and architecture at a high level, with diagrams if needed. Also discuss the alternatives that were considered but not chosen. | 2026-10-23 | 2026-10-24 | Dang |  | Completed
41 | Write Product Backlog section | Break the project into deliverable items and plan their order. | - List the tasks for the full project. - Each item has a business value (priority), its dependencies and the sprint it is planned for. - Show what is expected in the Alpha release (Project A) and the Beta release (Project B). | 2026-10-23 | 2026-10-24 | Hieu |  | Completed
42 | Write Quality Plan section | Define the quality standard and how it will be assured. | Describe the target quality of the deliverables, the quality assurance steps and the planned testing. | 2026-10-23 | 2026-10-24 | Ny |  | Not Yet
43 | Write Research and Investigation section | Show the research behind the analysis and design decisions. | Outline the research done on the application domain, similar existing systems, architecture styles and patterns, technology platforms, programming languages, sensors and so on. | 2026-10-23 | 2026-10-24 | Khai |  | Not Yet |  | Each member must be at least one research
44 | Write Skills Analysis section | Check that the team has the skills the chosen design requires. | - Map the knowledge, skill and technology requirements of the architecture to the team’s skills. - Highlight any gaps and give a plan to close them. | 2026-10-23 | 2026-10-24 | Minh Hoang |  | Completed
45 | Write Ethical Considerations section | Make sure the project follows relevant ethical rules and laws. | Review the ethical protocols, standards and Acts that apply (e.g. the Australian Privacy Principles, or health data and AI ethics), and explain how the project will comply. | 2026-10-23 | 2026-10-24 | Nhat Hoang |  | Completed
46 | Attach File Project Proposal and Project Charter to the Confluence workspace. | To centralize core project governance documentation by uploading and integrating the official Project Proposal and Project Charter into the team's Confluence workspace, ensuring full accessibility, version transparency, and alignment across all team members and stakeholders. | Upload and configure the foundational project management documents within the Confluence cloud sandbox. Key deliverables include: - Document Upload: Attach the finalized Project Proposal and Project Charter files (PDF/Word format) to the designated root/parent page in the Confluence space (e.g., VIB-Mock-Knowledge). - Page Structuring & Embedding: Format the Confluence page to display document previews/downloads cleanly, adding a brief summary section for quick reference by team members and advisors. - Access & Indexing Check: Ensure permissions are properly set so all project contributors can view/download the files, laying the groundwork for future knowledge ingestion workflows. | 2026-10-23 | 2026-10-24 | Ny | Confluence | Not Yet |  | Use '/' in the Confluence and attach file...

## Project_Schedule
PROJECT PLAN
| PROJECT TITLE |  | START DATE
| Internal Assistant for Enterprise Knowledge (Slack App Bot) |  | 2026-09-14 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
| Mr. Truong Ngoc Gia Hieu |  | 2026-12-06 |  |  | 84
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1.0 | **Phase I: Initiation, Proposal Iteration and Charter Alignment** | Complete | Team | 2026-09-14 | 2026-10-18 | 35 | Week 1–5: Proposal revised per tutor feedback & signed off by Mr. Phat | Not Started
1.1 | Requirements Exploration and Architecture Research | Complete | Team | 2026-09-14 | 2026-09-27 | 14 | Week 1–3: Scoping session with Sponsor & RAG research | In Progress
1.2 | Initial Discussion and Scoping Session | Complete | Team | 2026-09-14 | 2026-09-20 | 7 | Week 1–2: Initial scoping session with Project Sponsor | Complete
1.3 | Research RAG Architecture and Vector DB Options | Complete | Team | 2026-09-21 | 2026-09-27 | 7 | Week 3: Selected Qdrant/FAISS & LangChain/LlamaIndex stack | Complete
1.4 | Project Proposal Drafting, Revision and Submission | Complete | Team | 2026-09-28 | 2026-10-18 | 21 | Week 4–5: Revised proposal sections (Summary to Team Requirements)
1.5 | Project Charter Formalization & Structuring | Complete | Team | 2026-10-02 | 2026-10-18 | 17 | Week 4–5: Completed Charter sections (Problem to Risks/Constraints)
1.6 | Final Review and Submission to Mr. Phat | Complete | Hieu | 2026-10-14 | 2026-10-18 | 5 | Week 5: Submitted final charter and proposal for sponsor review/signature |  | Meeting Client
2.0 | **Phase II: System Architecture Design & Environment Setup** | In Progress | Team | 2026-10-19 | 2026-10-25 | 7 | Week 6: Active Execution Window & Stack Finalization | Meeting | Date | Time
2.1 | Repository Initialization & Team Onboarding | Complete | Team | 2026-10-12 | 2026-10-18 | 7 | Week 5: GitHub repo created by Gia Hiếu, all members added, branching setup | 1 | 2026-09-29 | 8.30PM - 9.30PM
2.2 | Write Project_Scheduled (Task 20) | Complete | Nhat Hoang | 2026-10-20 | 2026-10-20 | 1 | Week 6: Established delivery timeline (revised 25 Oct: Phases III-IV build in Weeks 7-10, Technical Specification in Weeks 11-12) & 4-layer architecture mapping | 2 | 2026-10-13 | 9PM - 10PM
2.3 | Design Layered Architecture (Task 21) | In Progress | Team | 2026-10-19 | 2026-10-25 | 7 | Week 6: Formalizing Presentation, Security/Auth, RAG Core, & Data Ingestion layers | 3/Team | 2026-10-22 | 7.30PM - 8.30PM
2.4 | Tech Stack, DWH & LLM Decision Matrix | In Progress | Team | 2026-10-19 | 2026-10-25 | 7 | Week 6: Deciding Data Warehouse platform, online vs offline SQL, and API vs custom LLM | 4
2.5 | Confluence Data Ingestion & REST Pipeline Strategy | In Progress | Team | 2026-10-19 | 2026-10-25 | 7 | Week 6: Ingesting via confluence.js / REST API -> HTML -> Markdown + image extraction | 5
2.6 | Security Requirements Clearance & Client Questions | In Progress | Gia Hieu | 2026-10-20 | 2026-10-25 | 6 | Week 6: Clarifying VIB email SSO validation, 2-tier RBAC (Employee/Admin), & mock data
2.7 | Slack & Confluence Sandbox & GitHub Branch Setup | Complete | Hieu / Team | 2026-10-22 | 2026-10-23 | 2 | Week 6: Created Confluence free space, Slack Bolt SDK Socket Mode app, and branch protection rules
2.8 | Project Document Writing (Sections 27–45) | In Progress | Team | 2026-10-23 | 2026-10-24 | 2 | Week 6: Team writing assignments (Cover page, Team Profile, Solution Approach, Product Backlog, Research)
3.0 | **Phase III: Delivery Phase 1 - Data Foundation, Slack Gateway & Security Middleware** | Not Started | Team | 2026-10-26 | 2026-11-08 | 14 | Weeks 7-8 (Sprint 2): backlog B1-B6, B11 - ingestion, vector store, Slack Socket Mode bot and deny-by-default access control
3.1 | Confluence REST API connector - fetch pages from mock/approved spaces (B1) | Not Started | Khai / Ny | 2026-10-26 | 2026-10-30 | 5 | Week 7: REST client, pagination, page metadata and restriction fields; source kept swappable (R5)
3.2 | Local vector DB, Docker dev environment & stack decision record (B2) | Not Started | Dang / Ny | 2026-10-26 | 2026-10-30 | 5 | Week 7: One minimal stack decision (Qdrant/FAISS vs pgvector), compose file, shared index snapshot (R8)
3.3 | Slack Bolt + Socket Mode bot: @mention -> threaded reply (B5) | Not Started | Minh Hoang / Khai | 2026-10-26 | 2026-10-30 | 5 | Week 7: Productionise the Task 27 prototype; tokens from environment; keep redacted reconnection evidence
3.4 | Channel whitelist middleware (deny by default) with negative tests (B6) | Not Started | Nhat Hoang / Minh Hoang | 2026-10-28 | 2026-11-01 | 5 | Week 7: Whitelist config plus blocked-channel / blocked-user tests (R10)
3.5 | Mock knowledge base in VIB-Mock-Knowledge: EN/VI prose, tables, images, restricted pages | Not Started | Ny / Khai | 2026-10-26 | 2026-11-01 | 7 | Week 7: Dataset agreed with Mr. Phat; basis for ingestion tests and the accuracy test set
3.6 | Sponsor check-in #1 - confirm test data, Confluence access and Technical Specification expectations | Not Started | Hieu | 2026-10-29 | 2026-10-29 | 1 | Week 7 (Thu): Fortnightly check-in (R15); confirm what the specification must contain for VIB deployment
3.7 | HTML -> clean Markdown converter for tables and macros, with parse-failure log (B3) | Not Started | Khai / Ny | 2026-11-02 | 2026-11-06 | 5 | Week 8: Depends on B1
3.8 | Chunking, multilingual (EN/VI) embedding and indexing pipeline (B4) | Not Started | Dang / Ny | 2026-11-04 | 2026-11-08 | 5 | Week 8: Depends on B2, B3; cited retrieval spike on mock data
3.9 | Slack SSO / identity validation middleware (B11) | Not Started | Nhat Hoang / Minh Hoang | 2026-11-02 | 2026-11-06 | 5 | Week 8: Identity from Slack sign-in only; not a bank authorisation (see Skills analysis)
3.10 | Interface contracts (Slack -> Security -> RAG) and mock-backed integration tests | Not Started | Nhat Hoang / Khai | 2026-11-05 | 2026-11-08 | 4 | Week 8: Working vertical slice reviewed before Week 9 integration
3.11 | Milestone M1: Phase 1 exit review (ingestion + gated bot demo) | Not Started | Hieu / Team | 2026-11-08 | 2026-11-08 | 1 | Week 8: Internal demo; go / no-go for RAG integration
4.0 | **Phase IV: Delivery Phase 2 - RAG Core, Slack Integration & Validation** | Not Started | Team | 2026-11-09 | 2026-11-22 | 14 | Weeks 9-10 (Sprint 3): backlog B7-B10, B12-B17 - retrieval, grounded answers, Slack integration and benchmarks
4.1 | Retriever and LLM integration - basic Q&A (B7) | Not Started | Dang / Ny | 2026-11-09 | 2026-11-13 | 5 | Week 9: Depends on B4
4.2 | Prompt templates with mandatory source citations and EN/VI query handling (B8, B9) | Not Started | Dang / Ny | 2026-11-11 | 2026-11-15 | 5 | Week 9: Strict citation prompt; language detection per query
4.3 | Slack message event handling linked to the RAG backend (B10) | Not Started | Minh Hoang / Nhat Hoang | 2026-11-11 | 2026-11-15 | 5 | Week 9: Depends on B5, B7
4.4 | Embedded image asset handling (B12) | Not Started | Khai / Ny | 2026-11-11 | 2026-11-15 | 5 | Week 9: Depends on B3; OCR scope to be confirmed with Mr. Phat
4.5 | Bilingual test query set with expected sources (preparation for B15) | Not Started | Ny / Dang | 2026-11-09 | 2026-11-15 | 7 | Week 9: Cases and pass criteria defined before benchmarking
4.6 | Sponsor check-in #2 - Phase 1 demo and Technical Specification outline approval | Not Started | Hieu | 2026-11-12 | 2026-11-12 | 1 | Week 9 (Thu): Agree specification outline and acceptance expectations
4.7 | Fallback reply for unanswerable queries (B13) and Block Kit answers with clickable sources (B14) | Not Started | Minh Hoang / Dang | 2026-11-16 | 2026-11-19 | 4 | Week 10: Depends on B7, B10
4.8 | Accuracy benchmark >=80% on the bilingual test set (B15) | Not Started | Ny / Dang | 2026-11-18 | 2026-11-22 | 5 | Week 10: Record sample size, configuration and failure analysis
4.9 | Latency benchmark <3 s and response caching (B16) | Not Started | Dang / Khai | 2026-11-18 | 2026-11-22 | 5 | Week 10: Measured on stated hardware (R7, R8)
4.10 | Security boundary tests - 100% whitelist compliance (B17) | Not Started | Nhat Hoang / Minh Hoang | 2026-11-18 | 2026-11-22 | 5 | Week 10: Non-whitelisted channels / users / documents must all be denied
4.11 | Technical Specification skeleton and component sections drafted as components land | Not Started | Hieu / Nhat Hoang | 2026-11-09 | 2026-11-22 | 14 | Weeks 9-10: Writing runs in parallel with the build so Weeks 11-12 are for consolidation and review
4.12 | Bug fixing, refactoring and Alpha build tag | Not Started | Team | 2026-11-20 | 2026-11-22 | 3 | Week 10: Code review of every open PR; tag Alpha build
4.13 | Milestone M2: Alpha code freeze (Phase 2 exit) | Not Started | Hieu / Team | 2026-11-22 | 2026-11-22 | 1 | Week 10: No new features after this date; only fixes required by the specification review
5.0 | **Phase V: Technical Specification Document & Handover to Mr. Phat** | Not Started | Team | 2026-11-23 | 2026-12-06 | 14 | Weeks 11-12 (Sprint 4): backlog B18 - specification sent to Mr. Phat for VIB deployment
5.1 | Spec Part A - Architecture, data flow and interface contracts | Not Started | Nhat Hoang / Minh Hoang | 2026-11-23 | 2026-11-27 | 5 | Week 11: Diagrams, layer responsibilities, Slack / security / RAG contracts
5.2 | Spec Part B - Ingestion and RAG design: schema, models, chunking, prompts, configuration | Not Started | Khai / Dang | 2026-11-23 | 2026-11-27 | 5 | Week 11: Reproducible settings for VIB engineers
5.3 | Spec Part C - Security, access control and privacy controls (whitelist, SSO, secrets, ethics) | Not Started | Nhat Hoang / Ny | 2026-11-24 | 2026-11-28 | 5 | Week 11: Maps controls to Privacy / data-protection obligations
5.4 | Spec Part D - Test and validation report: accuracy, latency, security results, known limitations | Not Started | Ny / Dang | 2026-11-24 | 2026-11-29 | 6 | Week 11: Measured results only; no claimed achievements without evidence
5.5 | Spec Part E - Deployment and operations guide for the VIB environment | Not Started | Minh Hoang / Khai | 2026-11-24 | 2026-11-29 | 6 | Week 11: Prerequisites, environment variables, Socket Mode vs HTTP Events hosting, monitoring, runbook
5.6 | Sponsor check-in #3 - walkthrough of the specification draft | Not Started | Hieu | 2026-11-26 | 2026-11-26 | 1 | Week 11 (Thu): Early feedback before the formal send
5.7 | Two-pass internal review and consolidation -> Technical Specification v1.0 | Not Started | Hieu / Team | 2026-11-30 | 2026-12-01 | 2 | Week 12: Peer review plus second-pass document check
5.8 | Milestone M3: Send Technical Specification Document to Mr. Phat | Not Started | Hieu | 2026-12-02 | 2026-12-02 | 1 | Week 12: Formal submission to the sponsor
5.9 | Sponsor review, Q&A and specification revisions (v1.1) | Not Started | Team | 2026-12-02 | 2026-12-05 | 4 | Week 12: Record decisions in meeting minutes
5.10 | Final demo, demo script and handover pack (repo tag, README, test evidence) | Not Started | Hieu / Team | 2026-12-04 | 2026-12-06 | 3 | Week 12: Final demonstration and handover package
5.11 | Milestone M4: Final handover and Project A submission | Not Started | Hieu | 2026-12-06 | 2026-12-06 | 1 | Week 12: End of Project A
5.12 | VIB deployment from the specification (outside team scope; timing set by VIB) | Not Started | Mr. Phat / VIB |  |  |  | Post-handover. Assumption to confirm with Mr. Phat: VIB engineers deploy using the Technical Specification
Formulas:
END DATE = MAX([END DATE, row below]:G35)
START DATE = MIN([START DATE, row below]:F35)

## Revision_Notes
REVISION NOTES - Projected schedule (25 Oct 2026)
A. What changed
Item | Previous plan | Revised plan
Weeks 7-8 | Phase III Ingestion & Security (Week 7); Phase IV RAG engine (Week 8) | Phase III - Delivery Phase 1: ingestion, vector store, Slack bot, whitelist and SSO (B1-B6, B11)
Weeks 9-10 | Phase V Slack integration (Week 9); latency / accuracy testing (Weeks 10-11) | Phase IV - Delivery Phase 2: RAG core, Slack integration, benchmarks and security tests (B7-B10, B12-B17); Alpha code freeze 22/11
Weeks 11-12 | Phase VI testing, packaging and handover | Phase V - Technical Specification Document written and sent to Mr. Phat (M3 = 02/12), review, final handover 06/12 (B18)
Sponsor check-ins | Not scheduled in the plan | Thursdays 29/10, 12/11, 26/11 (fortnightly, R15)
WBS numbers | Several WBS numbers were converted to dates by the d.m format | Rewritten as text (1.1, 2.1 ...)
Dates and durations | Hard-coded durations; project end date 08/01/2027 | Durations are formulas; project start / end now derive from the task rows (end 06/12/2026)
Gantt chart | Chart used an axis that started in Dec 2023 | Chart rebuilt below the task table with axis 14/09-07/12/2026
B. Assumptions to confirm with Mr. Phat
# | Assumption | Why it matters
1 | VIB engineers deploy the system from the Technical Specification (the team does not deploy in VIB production). | Sets Project A scope and the content of the deployment guide (row 5.12).
2 | The specification is written in English, with Vietnamese summaries on request. | Affects writing effort in Weeks 11-12.
3 | Delivery Phase 1 = Phase III (Weeks 7-8) and Delivery Phase 2 = Phase IV (Weeks 9-10). | Naming used in the Word plan and this workbook.
4 | All Alpha backlog items B1-B17 stay in scope; Sprint 3 (Weeks 9-10) is the heaviest sprint. | Risk R13; B12 and B14 are the first candidates to cut if behind.
5 | Bilingual test set size (proposed >=50 questions) and the mock dataset are agreed in the 29/10 check-in. | Needed for the 80% accuracy target.